Project Management
# Directions
Complete the simulation found on the Assignment Manager page on the Pearson site.
## Suggestions
- For each activity, calculate the cost to expedite/crash each day
- Look at the critical path activities first
  - Obsessively obsess over the critical path
- Save some money for unplanned events during the building process
# Questions
1. What were the following results for the completed project?
  1. Project cost
    1. $162,199.00
  2. Project profit/loss in $ and %
    1. $17,801.00
  3. Project completion time
    1. 126
  4. Project status (days over/under)
    1. +1 day
  5. Decision accuracy
    1. Medium
2. What was the original critical path? How did it change as tasks were expedited/crashed?
  1. The original critical path got stuck up on framing, and painting, however after these processes switched to better contractors or were expedited, I was able to increase the speed of the project.
3. How was it decided which tasks to expedite/crash?
  1. Tasks which made up a part of the critical path were all evaluated to find the best value in number of days saved for the money.
4. What was the homeowner morale? What factors impacted this?
  1. Homeowner morale was the representation of how on time I was. Since most of the project up until the end was ahead of schedule, my morale was fairly high.
5. Were the goals reached for the simulation? If not, how could it have been improved? If yes, then what was done that led to the success?
  1. I think the goals were reached for the simulation. I was able to produce the product near the time expected for near the cost I had expected.
# Overview

## Summary Screen

## Results­ – General Feedback

## Financial Analysis

## Decision Analysis